## Detailed
Module | Sub-Module | URS | API | UI Development | Testing | Backend | UI | Deployment Date
Login | Login | Done | Done |  | Done | Srikanth | Haris
| Authentication |  | Done |  | Done | Srikanth | Haris
| Authorization & Access Control |  | Code Review done |  | Done | Srikanth | Haris
| Logout | Done |  | Not Done | Done | Srikanth | Haris
| Logout Session | Done |  | Not Done | Not Done | Srikanth | Haris
User & Group | CRU for users | Done | Done |  | Done | Srikanth | Haris | 1st March | Srikanth & Haris | Priority | Internal Delivery Date | Customer Delivery Date | Ownership
| Sorting | Done | Done |  | Done | Srikanth | Haris |  |  | User Module | 28th Feb | 1st March | Srikanth
| Search and Filter (Search as you type and Wildcard search) | Done | Done | Not done | Done | Srikanth | Haris |  |  | Contract Module | 5th March | 7th March | Srikanth/Jenish
| CRU for user groups and role priveleges | Done | Done |  | Done | Srikanth | Haris |  |  | Notification Part 1 | 5th March | 7th March | Jenish/Hitesh
| Update Group |  | Done |  | Done |  |  |  |  | Settings | 7th March | 9th March | Hitesh
| Sorting | Done | Done |  | Done | Srikanth | Haris |  |  | Asset Module | 7th March | 12th March | Hitesh
| Search and Filter (Search as you type and Wildcard search) | Done | Done | Not done | Done | Srikanth | Haris |  |  | Staff Module | 7th March | 12th March | Hitesh
| Assign user to role in group | Done | Done |  | Done | Srikanth | Haris |  |  | Notification Part 2 | 14th March | 19th March | Jenish/Hitesh
| Remove user from group | Done | Done |  | Done | Srikanth | Haris |  |  | Search and Filter (Search as you type and Wildcard search) | 14th March | 19th March | Hitesh
| Sorting | Done | Done |  | Done | Srikanth | Haris |  |  | Dashboard | 14th March | 19th March | Hitesh/Jenish
| Search and Filter (Search as you type and Wildcard search) | Done | Done | Not done | Done | Jenish | Haris
| View My Profile (6.1.2.4) |  | Done | Not done | Done | Jenish | Haris
Contracts | CRUD for Contracts | Done | Done |  | Done | Srikanth | Haris | 5th March | Jenish & Haris
| Renewing Contracts | Done | Done | Not done | Done | Srikanth | Haris
| Maker Checker Flow for Add/Update Contracts | Done | Done |  | Done | Srikanth | Haris
| Maker Checker Flow for Delete Contracts | Done | Done |  | Done | Srikanth | Haris
| Expiry Calender | Done |  | Not done | Done | Srikanth | Haris
| Contract Summary (No.of Contracts based on status) | Done | Done | Not done | Done | Jenish | Haris
| Sorting (6.2.10) | Done | Done |  | Done | Jenish | Haris
| Search and Filter (Search as you type and Wildcard search)(6.2.9) | Done | Done | Not done | Done | Jenish | Haris
| Download | Done |  | Not done | Done | Srikanth | Haris
| Multiple File upload and Delete (Allow user to upload and remove files (excel, pdf, word etc.)) | Done |  | Not done | Done | Srikanth | Haris
Asset | CRUD for Asset | Done | Done |  | Done | Hitesh | Haris | 1st March EOD | Hitesh and Haris
| Renewing Asset | Done | Done | 1st March | Done | Hitesh | Haris
| Expiry Calender | Done | Done |  | Done | Hitesh | Haris
| Asset Summary (No.of Asset based on status) | Done | Done | 1st March | Done | Hitesh | Haris
| Sorting | Done | Done |  | Done | Hitesh | Haris
| Search and Filter (Search as you type and Wildcard search) | Done | Done | 2nd March | Done | Jenish | Haris
| Download | Done | Done | 2nd March | Done | Hitesh | Haris
| Multiple File upload and Delete (Allow user to upload and remove files (excel, pdf, word etc.)) | Done | Done | Not done | Done | Hitesh | Haris
Staff Module | CRUD for Staff | Done | Done |  | Done | Hitesh | Haris | 5th March EOD | Hitesh and Janardhan
| Renewing Staff | Done | Done |  | Done | Hitesh | Haris
| Expiry Calender | Done | Done |  | Done | Hitesh | Haris
| Staff Summary (No.of Staff based on status) | Done | Done | Not done | Done | Hitesh | Haris
| Sorting | Done | Done |  | Done | Hitesh | Haris
| Search and Filter (Search as you type and Wildcard search) | Done | Done | Not done | Done | Jenish | Haris
| Download | Done | Done |  | Done | Hitesh | Haris
| Multiple File upload and Delete (Allow user to upload and remove files (excel, pdf, word etc.)) |  | Done | Not done | Done | Hitesh | Haris
Settings | Staff: CRUD for R1/R2/R3 reminder for each Record to Monitor |  | Done | Done | Done | Hitesh | Haris | 28th Feb | Hitesh and Janardhan
| Staff: CRUD for staff particulars |  | Done | Done | Done | Hitesh | Haris
| Asset: CRUD for R1/R2/R3 reminder for Asset type and sub type |  | Done | Feb 27th | Done | Hitesh | Haris
| Asset: CRUD for Asset Location |  | Done | Feb 26th | Done | Hitesh | Haris
| Contracts: CRUD for R1/R2/R3 reminder |  | Done | Feb 27th | Done | Srikanth | Haris
Dashboard | View Staff, Asset and Contract Expiry reminders |  | Done | Not done | Done | Jenish | Haris
| Swagger Implementation |  | Done |  | Done | NA | Haris
Remaining Items
Dashboard | View Staff, Asset and Contract Expiry reminders |  | Done
Notifications | Sending Email to respective users, user groups and cc list |  | Done | Not done | Done | Jenish | Haris |  | Hitesh/Jenish & Janardhan
| Mail sending |  | Done | Not done | Done | Jenish | Haris
| Internal Bugs |  |  |  | Done
Client Bugs
Performance Issues (If Any)
| CR from customer |  | Not Yet Started
| Audit Tables (Triggers and Logging as required) |  | Initial Setup
| Encryption Decryption in Staff |  | Initial Setup

## IterationPlan (hidden)
Deliverables |  | API | UI | Testing
Week 1 | 4-8 Dec | : APIs for users : Update APIs as per change in ER Diagram | : Common Grid to be used : User & Group Users Groups My Group | : Update Test Cases for Contract and user module : Start on Assets
Week 2 | 11-15 Dec | : CRUD APIs for User Module: Users, groups and group roles : CRUD APIs for Reminder Table : Deployment | : User form Create and Edit : Groups form create : Settings UI Design | : Test cases for Contract : Test cases for Assets : Updated test cases for user module
Week 3 | 18-22 Dec | : Mapping with module type in groups : Group Role- Action type relation APIs for contracts and maker checker flow APIs for Notifications | : Search Design : My Group : Assign Group | : Test cases for Settings and Notifications : Test Cases for staffs : Test Cases for Settings : Review by Abhishek
Week 4 | 26-29 Dec | APIs for Asset APIs for Notifications and Settings | : Contract | : Testing for contracts
Week 5 | 1-5 Jan | APIs for Asset and Staff Module | : Asset : Setting | : Testing for contracts : Testing for User Module
Week 6 | 8-12 Jan | APIs for Staff module APIs for Dashboard | Staff Dashboard | : Testing for Asset : Testing for Setting : Test cases for Dashboard
Week 7 | 15-19 | Overall Integration | Overall Integration | : Testing for Staff and overall testing

## ProjectPlan (hidden)
| 2017-10-02 | 2017-10-09 | 2017-10-16 | 2017-10-23 | 2017-10-30 | 2017-11-06 | 2017-11-13 | 2017-11-20 | 2017-11-27 | 2017-12-04 | 2017-12-11 | 2017-12-18 | 2017-12-25 | 2017-01-01 | 2017-01-08 | 2017-01-15 | 2017-01-22 | Development-QA Complete | 2017-01-29 | 2017-02-05 | 2017-02-12 | 2017-02-19 | 2017-02-26 | 2017-03-05 | 2017-03-12 | 2017-03-19 | 2017-03-26
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 |  | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Kick Off | ●
Requirement Gathering
System & UI Design
Framework Setup
Setup at PSA
User Management
Contract Management
Equipment Management
Staff Management
Settings
Dashboard
Notification
SIT
UAT
Penetration Test
Go Live | [23 empty] | ●

## Sheet4 (hidden)
POST /createUser --createUser
DELETE /deleteUser/{userId}-- deleteUser
PUT /updateUser --updateUser
GET /user/{userId} --getUserById
GET /users--getAllUsers
GET /writeUsersToCSV –getDataForCsv