## Info
Project:
Test URL: | http://rs365-test.marine.psa:8080/Reminder365/
http://10.114.72.44:8080/Reminder365/
Release History
Version | Deployed By | Release Date
20180206 | Sourabh | 06/02/2018
20180221 | Wensi | 21/02/2018
20180307 | Sourabh | 08/03/2018
v0.5 | Sourabh | 2018-03-13
v0.6 | Wensi | 20/03/2018
v0.6.3 | Wensi | 21/03/2018
Revision History
Version | Prepared By | Date
1.0 | Wensi | 07/02/2018
1.1 | Wensi | 08/03/2018
1.02 | Wensi | 14/03/2018
1.03 | Wensi | 2018-03-21

## Summary
SubMod | MainMod
| Auth | UserGroup | Contract | Asset | Staff | Settings | Notification | Dashboard | Performance | General | Others
| General | General | General | General | General | General | General | General | General | General | General
| Login | User | Create | Create | Create | Contract Default Rem | Reminder | Summary by Module |  | Logging
| Logout | Group | View | View | View | Asset Default Rem | Expiry | Summary by User Group |  | Coding
| Session Timeout | Access Control | Update | Update | Update | Asset Types | Maker Checker | Expiry Calendar |  | Database
|  | My Group | Delete | Delete | Delete | Asset Locations |  |  |  | Err/Alert Msg
|  |  | Renew | Renew | Renew | Staff Default Rem |  |  |  | Consistency
|  |  | MakerChecker | Expiry Calendar | Expiry Calendar | Staff Particulars |  |  |  | A/C/S
|  |  | MC-Add | Record Summary | Record Summary | Staff Record Types |  |  |  | Server
|  |  | MC-Update | Search, Sort, Filter | Search, Sort, Filter
|  |  | MC-Delete | Download | Download
Expiry Calendar
Record Summary
Search, Sort, Filter
Download
Status | Category
| Issue | Bug | Enhancement | Clarification | CR
| Open | Open | Open | Fixed | Closed
| Fixed | Fixed | Enhanced | Clarified | Invalid
| Closed | Closed | Closed | Fixed
| Invalid | Invalid | Invalid | Invalid
Severity
High
Medium
Low
Feedback Summary
Category | Issue | [6 empty] | Bug | [6 empty] | Enhancement | [6 empty] | Clarification | [5 empty] | CR
MainMod \ Status | Open |  |  | Fixed | Closed | Invalid | Total | Open |  |  | Fixed | Closed | Invalid | Total | Open |  |  | Fixed | Closed | Invalid | Total | Open |  |  | Clarified | Invalid | Total | Open |  |  | Invalid | Total
Severity | High | Medium | Low |  |  |  |  | High | Medium | Low |  |  |  |  | High | Medium | Low |  |  |  |  | High | Medium | Low |  |  |  | High | Medium | Low
Auth | 1 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UserGroup | 0 | 0 | 0 | 1 | 19 | 0 | 20 | 0 | 0 | 0 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract | 1 | 1 | 0 | 0 | 11 | 0 | 13 | 4 | 0 | 0 | 0 | 6 | 0 | 10 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Asset | 0 | 1 | 0 | 0 | 2 | 0 | 3 | 0 | 1 | 0 | 1 | 6 | 0 | 8 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Staff | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 0 | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Settings | 0 | 2 | 0 | 1 | 1 | 0 | 4 | 0 | 0 | 2 | 0 | 3 | 0 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Notification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dashboard | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Performance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
General | 2 | 6 | 2 | 0 | 8 | 0 | 18 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Others | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 4 | 16 | 2 | 2 | 42 | 0 | 66 | 4 | 3 | 2 | 1 | 34 | 0 | 44 | 0 | 3 | 0 | 2 | 7 | 0 | 12 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
*Notes
Category | Defination
Issue | Requirements are not fulfilled, misunderstanding of requirements, inconsistent design/implementation, not user friendly, etc..
Bug | Problem caused by developers unintentionally
Enhancement | Features that can be enhanced to provide beter user experience
Clarification | Question and doubt
CR | Change Request

## R365
| Module |  | Description | Category | Severity | Status | Test |  | Verify |  | Test Evidence |  | Comments
| Main | Mod |  |  |  |  | Date & By | Release | Date & By | Release |  | Assigned to | PSAM | Saksoft
1 | Auth | Login | Observation: when user login, password is printed in clear text Expectation: password should not be printed in clear text | Issue | High | Closed | 06/02/2018 Wensi | 20180206 |  | 20.03.18 | #1.PNG |  | QA: Issue Fixed - https://www.screencast.com/t/NMdubxL4Ot | 12/03/2018 QA: Not occurring now 20/03/2018 QA: Issue Fixed - https://www.screencast.com/t/NMdubxL4Ot
2 | Auth | Login | Observation: At login page, if user hasn't keyin username / password, user is not allowed to click LOGIN button. However, error message is not clearly shown. --> User may not be clear about what is happening, Expectation: App should show error message clearly when user hasn't keyed in proper username / password. | Enhancement | Medium | Closed | 06/02/2018 Wensi | 20180206 |  |  | #2.PNG |  |  | 02.04.2018 QA: Issue is fixed
3 | Auth | General | Observation: "Forgot Password?" dialogue will only be closed when user clicks the "x" icon Expectation: "Forgot Password?" dialogue should also be closed when user click outside of the dialogue. | Enhancement | Medium | Closed | 06/02/2018 Wensi | 20180206 |  | 20.03.18 |  |  | QA: Issue Fixed - https://www.screencast.com/t/tAw1woGLQ | 20/03/2018 QA: Issue Fixed - https://www.screencast.com/t/tAw1woGLQ
4 | Auth | General | Observaztion: When user keys in wrong username / password, and then click LOGIN button repeatedly, the same error messages are shwon on the screen repeatedly Expectation: Duplicate error message should not be shown on screen | Enhancement | Medium | Closed | 06/02/2018 Wensi | 20180206 |  | 20.03.18 | #4.PNG |  | QA: Issue Fixed - https://www.screencast.com/t/dulUAqSlV | 20/03/2018 QA: Issue Fixed - https://www.screencast.com/t/dulUAqSlV
5 | Auth | Login | Observation: Username and password is always automatically remembered by browser, user has no option to unsave the password Expectation: Provide a checkbox for user to choose to save or unsave password at login page. | Issue | High | Open | 07/02/2018 Wensi | 20180206 |  |  | #5.png |  | This requires remember me functionality | 12/03/2018 Requires Remember Me functionality
6 | General | Record Summary | Observation: When click the arrow icon of the summary boxes (e.g. "No. of Contracts Expired", "No. of Contracts Expiring This Month","No. of Contracts Expiring Next Month", etc...), user will be redirected to login page | Bug | High | Closed | 07/02/2018 Wensi | 20180206 |  |  |  |  | Verification to be done in respective modules | 12/03/2018 Implemented Module wise, review in Asset and Staff and respective if bug persists it can be opened 20/03/2018 Verification to be done in respective modules
7 | General | General | Observation: Whenever user clicks browser refresh button (e.g. on dashboard, contract list page, etc), user will see "Access Denied" error Expectation: User shall be able to refresh page | Issue | High | Closed | 07/02/2018 Wensi | 20180206 |  | 20.03.18 | #7.PNG |  | QA: Issue Fixed - https://www.screencast.com/t/4QxCffqq5VIs Note: Page gets blank, instead of access denied error message(For this issue is raised) | 20/03/2018 QA: Issue Fixed - https://www.screencast.com/t/4QxCffqq5VIs Note: Page gets blank, instead of access denied error message(For this issue is raised)
8 | Contract | General | Observation: Calendar popup is only closed when user clicks on the calendar icon, but not closed when user click on outside of the input field. Expectation: Expect calendar pop up to be closed when calendar popup lose focus | Enhancement | Medium | Closed | 07/02/2018 Wensi | 20180206 |  | 20.03.18 | #8.PNG |  | QA: Issue Fixed - https://www.screencast.com/t/Ap8wlxvNI | 20/03/2018 QA: Issue Fixed - https://www.screencast.com/t/Ap8wlxvNI
9 | Contract | General | Observation: no error message is shown when reminder dates are later than expiry date. User is able to create a contract reminder whose reminder dates are later than expiry dates Expectation: 1st, 2nd and 3rd reminder dates shall not be later than expiry date. Expriy message shall be shown properly | Bug | High | Closed | 07/02/2018 Wensi | 20180206 |  | 20.03.18 | #9.PNG | Haris/Jana | QA: Issue still exist for Staff Reminder Module - https://www.screencast.com/t/Bi0BKwwOeZ | 20/03/2018 QA: Issue still exist for Staff Reminder Module - https://www.screencast.com/t/Bi0BKwwOeZ | 29/03/2018 QA: Issue is fixed https://www.screencast.com/t/9januA5y
10 | Contract | General | Observation: Confirmation message "Contract has been added to Reminder365 successfully" is shown when a contract is created successfully. However, contract reminder number is not included in confirmation message. Expectation: Contract reference number shall be included in confirmation message whenever possible. Please show confirmation message after contract is added/update/deleted/resubmitted ... in following format Contract {contract ref number} is {action}ed and waiting for verification. E.g. Contract CONT1234 is added and waiting for verification. Contract CONT1234 is edited and waiting for verification. Contract CONT1234 is deleted and waiting for verification. Contract CONT1234 is resubmitted and waiting for verification. Contract {contract ref number} is {action}ed successfully E.g. Contract CONT1234 is verified successfully. Contract CCNT1234 is rejected successfully. | Issue | Medium | Closed | 07/02/2018 Wensi | 20180206 |  | 20.03.18 | #10.PNG |  | QA: Issue is fixed - https://www.screencast.com/t/ZadyfmZOVUU8 | 20/03/2018 QA: User is not able to create contracts(Bug ID - Contract tab - 50) : https://www.screencast.com/t/KDa6Udg0X
11 | Contract | General | Observation: in create reminder page, user is unable to click "submit" button if there are validation error. No error message is shown. User is unclear about what is happening. Expectation: Allow user to click "SUBMIT" button when there is invalid data, app shall show error message properly after user clicks "SUBMIT" button | Issue | Medium | Open | 07/02/2018 Wensi | 20180206 | [5 empty] | Discuss flow with client | AS: Add message on click of Submit button as 'Please fill in the Mandatory Fields marked as '*' before final submission! '
12 | Contract | Expiry Calendar | Observation: Expiry calendar function is not ready yet - not default to current month - < > button is not working - dates and weekdays don't match - etc | Issue | High | Closed | 07/02/2018 Wensi | 20180206 |  | 20.03.18 | #12.PNG | Jenish | QA: Issue still exist - https://www.screencast.com/t/5rHYdcpe | 20/03/2018 QA: Issue still exist - https://www.screencast.com/t/5rHYdcpe | 29/03/2018 QA: Issue is fixed - https://www.screencast.com/t/hy8GCN9fR
13 | Contract | Expiry Calendar | Observation: There is a "-" and "x" icon on Expiry Calendar. However, there is not effect when user clicks "-" and "x" icon Expectation: "-" and "x" is not required | Issue | Medium | Closed | 07/02/2018 Wensi | 20180206 |  | 20.03.18 | #13.PNG |  | QA: Removed "-" and "x" icon on Expiry Calendar | 20/03/2018 QA: Removed "-" and "x" icon on Expiry Calendar
14 | Contract | General | Observation: When user clicks Submit button on create page, following confirmation dialogue is shown: "Contract "abc" will be created! Confirm to continue. [NO][YES]" Expectation: Please show confirmation dialogue in following format: "You are going to {action} Contract {contract_num}. Click OK to continue." [CANCEL] [OK] e.g. You are going to Add Contract CONT1234. Click OK to continue. [CANCEL] [OK] You are going to Edit Contract CONT1234. Click OK to continue. [CANCEL] [OK] You are going to Delete Contract CONT1234. Click OK to continue. [CANCEL] [OK] You are going to Verify Contract CONT1234. Click OK to continue. [CANCEL] [OK] You are going to Reject Contract CONT1234. Click OK to continue. [CANCEL] [OK] | Enhancement | Medium | Closed | 07/02/2018 Wensi | 20180206 |  | 20.03.18 |  |  | QA: Bug is fixed now
15 | Contract | General | Observation: Fields "Savings Currency & Contract" and "Contract Currency & Value" require 2 decimal places. However, the place holders for them are "000" and "00" respectively, which might be confusing to user Expectation: Please use placeholder "00.00" for these two fields | Issue | Medium | Closed | 07/02/2018 Wensi | 20180206 |  | 20.03.18 | #15.PNG |  | QA: Issue fixed - https://www.screencast.com/t/mdFQdTEHY | 20/03/2018 QA: Issue fixed - https://www.screencast.com/t/mdFQdTEHY
16 | Contract | General | Observation: Confirmation dialogue "You have unsaved data!, Do you want to leave?" is shown if user going to leave current edit page. Expectation: Display following message in confirmation dialogue instead: "You are going to leave this page without saving any information. Click OK to continue. [CANCEL] [OK]" | Enhancement | Medium | Closed | 07/02/2018 Wensi | 20180206 |  | 20.03.18 |  |  | QA: Issue fixed - https://www.screencast.com/t/NU6yr5A5eZwW | 20/03/2018 QA: Issue fixed - https://www.screencast.com/t/NU6yr5A5eZwW
17 | Contract | Create | Observaton: In create page, "Active" is default to "NO" Expectation: Please default "Active" to "Yes". See URS 6.2.1 | Issue | Medium | Closed | 07/02/2018 Wensi | 20180206 |  | 20.03.18 |  |  | QA Issue fixed | 20/03/2018 QA Issue fixed
18 | Contract | MakerChecker | Observation: Checker is able to edit details of a "pending-verification" contract Expectation: A checker shall only be able to verify or reject a contract. He shall not be able to edit the contract details | Issue | High | Closed | 07/02/2018 Wensi | 20180206 |  | 20.03.18 |  |  | AS: Will implement QA: Issue is fixed - https://www.screencast.com/t/owVrvQ4Oha1 | 20/03/2018 AS: Will implement QA: User is not able to create/ edit/ renew contracts(Bug ID - Contract tab - 50) : https://www.screencast.com/t/KDa6Udg0X
19 | Contract | General | Observation: Created By, Created Date, Last Modified By, Last Modified Date is missing from view, update, review page Expectation: Created By, Created Date, Last Modified By, Last Modified Date shall be shown in view, udpate, and review page. see URS | Issue | High | Closed | 07/02/2018 Wensi | 20180206 |  | 20.03.18 |  | Test with new data | QA: Fixed only for Contract, issue still exist for Asset and Staff - https://www.screencast.com/t/hlCOhQNq | 20/03/2018 QA: Fixed only for Contract, issue still exist for Asset and Staff - https://www.screencast.com/t/hlCOhQNq | 29/03/2018 QA: Now Created By, Created Date, Last Modified By, Last Modified Date fields are showing on view, edit page of Assest, Straff and Contract. https://www.screencast.com/t/IgaccSJv
20 | Contract | General | Observation: For all Date fields, placeholders are DD/MM/YYYY. However, after pickup a date from calendar, date are in YYYY-MM-DD format Expectation: Please make placeholder and user input consistent | Issue | Medium | Closed | 07/02/2018 Wensi | 20180206 |  | 20.03.18 | #20.PNG |  | QA: Issue fixed | 20/03/2018 QA: Issue fixed
21 | Contract | MakerChecker | Observation: When click "Reject" button on reivew contract page, Following popup will be shown: ------------------------------------------------------------------------------ REJECT MESSAGE Contract Title: (readonly) Contract Reference Number: (readonly) Message To: (textfield) Remarks: (textarea) [SEND MESSAGE] ------------------------------------------------------------------------------ Analysis: Rejection Remarks will be shown in contract review page after a contract is rejected, rather than notification email (see email template), so "Message To" field and "Send Message" button are not relevent. Expectation: when user clicks "Reject" button, app shows following popup box ------------------------------------------------------------------------------ Reject Contract You are going to reject Contract ContNumABC. Please key in Rejection Remarks, and click OK to continue. Rejection Remarks: (textarea) [CANCEL] [OK] ------------------------------------------------------------------------------ | Issue | Medium | Closed | 07/02/2018 Wensi | 20180206 |  | 20.03.18 |  |  | QA: Issue is fixed - https://www.screencast.com/t/ATwMxpv64b
22 | Contract | MakerChecker | Observation: In review contract page, message such as "This contract is created by Harry Lim on 07/02/2018 13:45. Please verify" is not shown. Expectation: Please display mesasge on review contract page in following format: This contract is {action}ed by {maker} on {date time}. Please review and verify. E.g. This contract is added by Harry Lim on 07/02/2018 15:47. Please review and verify. | Issue | Medium | Closed | 07/02/2018 Wensi | 20180206 |  | 20.03.18 |  |  | QA: Issue fixed - https://www.screencast.com/t/23l4r6LR | 20/03/2018 QA: Issue fixed - https://www.screencast.com/t/23l4r6LR
23 | Contract | MC-Add | Observation: Step1: maker adds contract Step2: checker rejects contract Step3: maker updates and resubmit contract Results: in contract review list, there is one contract with status "Rejected" and one contract with status "New" Step4: maker delete "Rejected" contract Results: in contract review list, there is one contract with status "Deleted" and one contract with status "New" Expectation: At Step3: the resubmitted contract shall overwrite the "Rejected" contract, so in contract review list, there is only one "New" contract with updated details. At Step4: after maker delete the "Rejected" contract, this rejected contract shall be removed from the system. | Issue | High | Closed | 07/02/2018 Wensi | 20180206 |  | 20.03.18 | #23.PNG |  | QA - Bug is fixed | 20/03/2018 QA - Bug ID - Contract tab - 50
24 | Contract | MC-Add | Observation: Step1: maker adds contract Step2: checker verified contract --> when user clicks "verify" button, there is no confirmation dialogue shown for user to confirm his action Expectation: Please show confirmation dialogue for user to confirm his action. refer to #14 | Bug | High | Closed | 07/02/2018 Wensi | 20180206 |  | 20.03.18 |  |  | QA: Bug is fixed- https://www.screencast.com/t/JufrVuoOjndE | 20/03/2018 QA: Nothing happens when we clicks on Verify button - https://www.screencast.com/t/uIVfEvh07
25 | Contract | MC-Update | Observation: Step1: maker creates contract Step2: checker verifies contract Step3: maker updates contract (update contract ref number) --> result: the original contract is missing in contract list. Expectation: The original contract shall still be in contract list, and the updated contract shall be in contract review list. see urs 6.2.6.2 | Bug | High | Closed | 07/02/2018 Wensi | 20180206 |  | 20.03.18 |  | Haris: Please verify | QA: Issue still exist - https://www.screencast.com/t/AwoJN6LEQ | 20/03/2018 QA- User is not able to create/ edit/ renew contracts(Bug ID - Contract tab - 50) : https://www.screencast.com/t/KDa6Udg0X | 29/03/2018 QA: Now The original contract is still showing in contract list, and the updated contract is showing in contract review list. https://www.screencast.com/t/CPzkarIea
26 | Contract | MC-Update | Observation: Step1: maker creates contract Step2: checker verifies contract Step3: maker updates contract (update contract title) Step4: checker verifies contract --> result: both the original contract and updated contract exist in contract list Expectation: Only the updated contract shall be shown in the contract list after the updated details are verified. | Bug | High | Closed | 07/02/2018 Wensi | 20180206 |  | 20.03.18 |  |  | QA: Only one contract displayed in contract list page and disappear from the Review page | 20/03/2018 QA- User is not able to create/ edit/ renew contracts(Bug ID - Contract tab - 50) : https://www.screencast.com/t/KDa6Udg0X
27 | Contract | MC-Delete | Observation: Step1: maker creates contract Step2: checker verifies contract Step3: maker deletes contract --> result: the original contract is missing in contract list. Expectation: The original contract shall still be in contract list, and the deleted contract shall be in contract review list. see urs 6.2.6.3 | Bug | High | Reopen | 07/02/2018 Wensi | 20180206 |  | 20.03.18 |  | Haris: Please verify | QA: Bug still exist - https://www.screencast.com/t/fFVxf6cBDm3i | 20/03/2018 QA - Bug ID - Contract tab - 50 | 29/03/2018 QA: bug still exist - https://www.screencast.com/t/RYAI5qrAXvdq
28 | Contract | MC-Delete | Observation: Step1: maker creates contract Step2: checker verifies contract Step3: maker deletes contract Step4: checker verifies contract deletion --> result: the original contract appears in contract list again.. Expectation: After contract deletion is verified, the contract shall be removed from the system | Bug | High | Closed | 07/02/2018 Wensi | 20180206 |  | 20.03.18 |  |  | QA: Issue is fixed - https://www.screencast.com/t/a5ZJVjr6meQ | 20/03/2018 QA - Bug ID - Contract tab - 50
29 | General | Coding | Observation: Environment-dependent configurations are set up in .war file Expectation: help to setup environment-dependent configurations in Jboss server instead of .war file Such as: - Data source configuration - LDAP configuration - File upload path - etc... The objective is to use the same war file in UAT and PROD environment without the need to repackage .war file. | Issue | Medium | Open | 19/02/2018 Wensi | 20180206 |  |  |  | Srikanth/Hitesh
30 | UserGroup | User | Observation: "Add User" button is not working. Brwoser console has error | Bug | High | Closed | 21/02/2018 Wensi | 20180221 |  | 20.03.18 | #30.PNG |  | QA- Issue fixed | 12/03/2018 QA: Can't verify, as video/ screenshot is not there in evidence folder 20/03/2018 QA- Issue fixed
31 | UserGroup | Group | Observation: Sometimes, the rows under Role Configuration is wrapped. Expectation: Column width shall be defined by %, and row shall not be wrapped under different resolution | Enhancement | Medium | Fixed | 21/02/2018 Wensi | 20180221 |  |  | #31.PNG |  |  |  | 29/03/2018 QA: png/ video is not there in evidence folder to verify
32 | UserGroup | User | Observation: Create User: After retrieving User ID from LDAP, user has to click "Edit" button before he can change the User ID. Expectation: After retrieving User ID from LDAP, if user wants to change user id, he shall not need to click the "Edit" button, this is an additional step for them. Expected Steps: 1) User key in user id and click retrieve button 2) User clicks on the user id field to direct change the user id 3) Scenario 1: User clicks on the retrieve button to get user details. Scenario 2: If user clicks the submit button without clicking the retrieve button, app shall show meaningful error message to remind user to do so. | Enhancement | Medium | Fixed | 08/03/2018 Wensi | 20180307 |  |  | #32.png | Haris | 02.04.2018 QA: Evidence is not there in evidence folders
33 | General | Err/Alert Msg | Observation: Style of alert messages are very different. Expectation: Please ensure consistency of alert message throughout the system | Issue | High | Closed | 08/03/2018 Wensi | 20180307 |  |  | #33.png
34 | UserGroup | User | Observation: Error message is not shown clearly when user attempts to create a user with duplicate user name Expectation: Meaningful error message shall be shown. | Issue | High | Closed | 08/03/2018 Wensi | 20180307 |  |  |  |  | AS: Haris why this is still open ? We saw it was corrected yesterday , H : I'm not able to change status , it is fixed QA: Verified and marked closed |  | 20/03/2018 QA: Verified and marked closed
35 | UserGroup | User | Observation: System allows to create users with the same user name. Expectation: System shall no allow creating users with the same user name. | Bug | High | Closed | 08/03/2018 Wensi | 20180307 |  |  | #35.png
36 | UserGroup | User | Observation: Edit User: in edit user page, record sequence number, rather than user id is shown. Expectation: User ID shall be shown in edit page. | Bug | High | Closed | 08/03/2018 Wensi | 20180307 |  |  | #36.png
37 | General | General | Observation: When app fetches data from system, the screen blinks with black backgroud flash out Expectation: Please make sure the action is smooth and fluent.. 13/03/2018 looks like this is because the dark Wait Screen is displayed for a short while. can we change the wait screen to brighter color? | Issue | Low | Closed | 08/03/2018 Wensi | 20180307 |  |  | #37.mp3
38 | UserGroup | User | Observation: In View User page, Create By, Updated By, Updated Date are always empty Expectation: System shall show be able to capture Created By/ Created Date, Updated By/ Updated Date properly. See urs for the Created Date/Updated Date format | Bug | Medium | Closed | 08/03/2018 Wensi | 20180307 |  |  | #38.png
39 | UserGroup | User | Observation: Update user: when update user details in Edit User page, updated details are immediately updated in the User List. User user click "x" to cancel the update action, updated details are still shown in UI List Expectation: Data shall not be updated in the system until user clicks Submit or Save button | Bug | High | Closed | 08/03/2018 Wensi | 20180307 |  |  | #39.mp3
40 | UserGroup | Group | Observation: Add Group: when user click "Add" button under the Group Administrator section, a pop up window is shown for user to select user. - The title of the popup window is "Add User". - DB sequence id is shown in User ID column Expectation: - "Add User" title is confusing, the title of the popup window shall be "Add Administrator" - User ID shall be shown under User ID column | Issue | Medium | Closed | 08/03/2018 Wensi | 20180307 |  |  | #40.mp3
41 | UserGroup | Group | Observation: Add Group: user is unable to add group if no group admin is assigned. However, no error message is shown. Expectation: App shall show display meaningful error message to user. | Issue | Medium | Closed | 08/03/2018 Wensi | 20180307 |  |  | #41.mp3 |  | H: Discussed with AS , Disabling submit/add button if no user is slected QA: AS per dev comments closing the bug |  | 12/03/2018 H: Discussed with AS , Disabling submit/add button if no user is slected QA: AS per dev comments closing the bug
42 | UserGroup | Group | Observation: Update Group: User update group admin from edit group page. However, the updated group admin is not reflected in the system. Expectation: Updated information shall be relected in the system | Bug | High | Closed | 08/03/2018 Wensi | 20180307 |  |  | #42.mp3
43 | UserGroup | Group | Observation: Delete Group: Sometimes unable to delete a group. There is no meaningful error message explaining why the group cannot be deleted. Browser console and Reminder.log has no log. Expectation: Please show meaningful error message so that user understand what is happening. Please provide sufficient server log so that it is easier to investigate the issue. 13/03/2018 in error message "Unable to delete Group584", db sequence number 584 is shown. --> please change it to group name | Issue | Medium | Closed | 08/03/2018 Wensi | 20180307 |  |  | #43.mp3
44 | UserGroup | My Group | Observation: My Group tab is shown even when login user is not a group admin of any group. Expectation: If the login user is not a group admin of any group, then My Group tab shall not be visible to him at all | Issue | Medium | Closed | 08/03/2018 Wensi | 20180307
45 | UserGroup | My Group | Observation: In search page, login user is the group admin of an Asset Group and a Contract Group. However, All "Asset" "Contract" and "Staff" are shown in "Select Module" dropdown list. Expectation: "Dropdown options are all the reminder modules available in the login user’s (Group Administrator) group(s)" Similar to the dropdown lists in Assign & Group page | Issue | Medium | Closed | 08/03/2018 Wensi | 20180307 |  | 20.03.18 |  |  | QA- Issue fixed |  | 20/03/2018 QA- Issue fixed
46 | UserGroup | My Group | Observation: In search page, after user select "Module" and "Group", no user is shown in the user list. User list is only shown when "Role" is selected. Expectation: If role is not selected, all users inside this group shall be shown in the group's user list. The objective is to allow the group admin to have a overview of the users in the group | Issue | Medium | Closed | 08/03/2018 Wensi | 20180307 |  |  | #46.mp3
47 | UserGroup | My Group | Observation: Search page, user select a different user role. However, search results are not changed. | Bug | Medium | Closed | 08/03/2018 Wensi | 20180307 |  |  | #47.mp3
48 | Asset | Create | Observation: Contract Groups are shown in User Group's dropdown list. Expectation: Asset Group shall be shown instead | Bug | High | Closed | 08/03/2018 Wensi | 20180307 |  |  | #48.mp3
49 | General | Consistency | Observation: Date placeholder is in the format of DD/MM/YYYY. However, actual format is YYYY-MM-DD Expectation: Please make sure the date format are consistent, refer to urs for date format | Issue | Medium | Closed | 08/03/2018 Wensi | 20180307 |  |  | #49.png |  | QA: I found the format in DD/MM/YYYY in URS |  | 12/03/2018 QA: I found the format in DD/MM/YYYY in URS
50 | Asset | Create | Observation: "Enter To List" and "Enter CC List" is shown as the placeholder of auto generated cc list and to list. Expectation: These two fields are auto generated, shall not show irrelevant placeholder | Issue | Medium | Closed | 08/03/2018 Wensi | 20180307 |  | 20.03.18 | #50.png |  | QA- Issue fixed |  | 12/03/2018 QA: This bug is still exist, placeholder is there 20/03/2018 QA- Issue fixed
51 | Asset | Search, Sort, Filter | Observation: Asset record is not turned to red after it is expired Expectation: Asset record shall turn to red after expiration | Bug | Medium | Closed | 08/03/2018 Wensi | 20180307 |  |  | #51.png
52 | Asset | View | Observation: User is unable to download those uploaded files. Expectation: User shall be able to download uploaded files. | Bug | High | Closed | 08/03/2018 Wensi | 20180307 |  |  |  |  | QA: Getting 404 error message while trying to download the uploaded files on View and Edit screen both |  | 12/03/2018 QA: Getting 404 error message while trying to download the uploaded files on View and Edit screen both
53 | Asset | View | Observation: User group is missing in view/edit group page. | Bug | High | Closed | 08/03/2018 wensi | 20180307 |  |  | #53.png |  | QA: Not occurring now |  | 12/03/2018 QA: Not occurring now
54 | Asset | Download | Observation: - File is downloaded in .csv format. - Some information in the downloaded file is not meaningful to user, such as "null", assetType "1", date "1520179200000" etc Expectation: - File shall be downloaded in excel format - Information in downloaded file shall be meaningful to user | Bug | High | Closed | 08/03/2018 Wensi | 20180307 |  |  | #54_assets.csv
55 | UserGroup | My Group | Observation: Assign role: when change role filter from "Group Admin" to something else, system will hang | Bug | Medium | Closed | 08/03/2018 Wensi | 20180307 |  | 20.03.18 | #55.mp3 |  | QA : Issue fixed |  | 12/03/2018 QA: Can't verify, video is not there in evidence folder 20/03/2018 QA : Issue fixed
56 | General | Logging | Observation: Audit table is not in database yet. Expectation: Refer to URS | Issue | High | Open | 13/03/2018 Wensi | v0.5 |  |  |  | Hitesh | Not yet implemented |  | 20/03/2018 Not yet implemented
57 | General | Logging | Observation: Application log is not detailed enough. E.g. When user login, only following two lines are shown in application log 2018-03-13 17:18:02 INFO GroupDAOImpl:978 - fetching group of user :1 2018-03-13 17:18:02 INFO GroupDAOImpl:978 - fetching group of user :1 Expection: Refer to URS | Issue | High | Open | 13/03/2018 Wensi | v0.5 |  |  |  | Hitesh | Need to check details. Section 9.1.2 |  | 20/03/2018 Need to check details. Section 9.1.2
58 | General | A/C/S | Observation: When use clicks the summary box on Asset/Contract/Staff module, search results are not filtered. Expectation: If user clicks the summary box, corresponding contract/asset/staff list will be shown in search results. Refer to URS "View Contract/Asset/Staff Summary" | Issue | Medium | Closed | 13/03/2018 Wensi | v0.5 |  |  |  |  | Fixed |  | 20/03/2018 Fixed
59 | UserGroup | User | Observation: View user: Created/Last Modified Date is shown in dd-mm-yyyy format. Expectation:"DD/MM/YYYY HH:MM:SS", refer to urs | Issue | Low | Closed | 13/03/2018 Wensi | v0.5
60 | UserGroup | User | Observiation: View user: the display of "Active", "Overall User Admin", "Overall Group Admin" is confusing Expectation: Please change to more meaningful representation | Issue | Medium | Closed | 13/03/2018 Wensi | v0.5 | 20.03.18 |  | #60.PNG |  | QA- bug fixed |  | 20/03/2018 QA- bug fixed
61 | UserGroup | User | Observation: Cancel update user takes too long time. | Issue | Medium | Fixed | 13/03/2018 Wensi | v0.5 |  |  | #61.pm4 |  | Check on customer machine |  | 20/03/2018 Check on customer machine 02.04.2018 QA: Have we checked on customer's machine?
62 | General | Err/Alert Msg | Observation: Alert message such as "You have unsaved data ! Do you want to leave ? [Cancel][OK]" --> [OK] button is highlighted in red, which my mislead user to click the [OK] button by mistake Expectation: Please highlight the [Cancel] button rather than [OK] button | Issue | Medium | Closed | 13/03/2018 Wensi | v0.5 | 20.03.18 |  | #62.png |  | QA: Issue Fixed - https://www.screencast.com/t/acQ06SFsM
63 | UserGroup | Group | Observation: Edit Group: when add group admin, db sequence is displayed under User ID Expectation: User id shall be displayed under User ID | Issue | Medium | Closed | 13/03/2018 Wensi | v0.5 |  |  | #63.mp4 |  |  |  | 29/03/2018 QA: Issue is fixed- https://www.screencast.com/t/Q0d2ChtyIwoW
64 | UserGroup | Group | Observation: tested with overall group admin "RS365_admin": if he is not a group admin of any group, he won't be able to view User & Group tab at left menu related to #44 Expectation: User shall be able to view user & group menu as long as he is an overall user admin, overall group admin, or a group admin of any group. | Issue | Medium | Closed | 13/03/2018 Wensi | v0.5 | 26.03.2018 |  |  |  |  | QA: Verified with credentials shared to us
65 | UserGroup | User | Observation: test with user "RS365_admin", user is able to create group, user even when user.group_admin=0 and user.user_admin=1. Expectation: only overall group admin shall be able to manage group, only overall user admin shall be able to manage user | Issue | High | Closed | 13/03/2018 Wensi | v0.5 | 20.03.18 |  |  |  | QA require credentials of RS365_admin | 20/03/2018 QA require credentials of RS365_admin | 02.04.2018 QA: Checked with our credentials and its working fine
66 | UserGroup | My Group | Observation: in My Group user list, no users are shown when module, group, and role are selected | Bug | High | Closed | 13/03/2018 Wensi | v0.5 | 19.03.18 |  | #66.mp4 |  | QA: Not occurring at our end | 20/03/2018 QA: Not occurring at our end
67 | Asset | Search, Sort, Filter | Observation: Sometimes, when user goes to Asset home page, no record is shown in asset list. However, if user clicks date on calendar, asset will be shown on the asset list | Bug | Medium | Closed | 13/03/2018 Wensi | v0.5 | 20.03.18 |  | #67.mp4 |  | QA- Bug fixed | 20/03/2018 QA- Bug fixed
68 | General | General | Observation: Expiry Calendar: When user mouses over the date on calendar, he may not know that the date is clickable. Expectation: Change the mouse to hand shape so that user knows that it is clickable | Enhancement | Medium | Closed | 13/03/2018 Wensi | v0.5 | 20.03.18 |  | #68.mp4 |  | Qa: Bug fixed | 20/03/2018 Qa: Bug fixed
69 | General | General | Observation: Sort: sort icon ↕ is not displayed in the header of sortable column, user may not know that the column is sortable. ( currently, ↑ or ↓ is displayed after user clicks the sortable column header) Expectation: please display ↕ in sortable column header, display ↓ or ↑ after the column is sorted. | Enhancement | Medium | Open | 13/03/2018 Wensi | v0.5 |  |  | #69,mp4
70 | Asset | Search, Sort, Filter | Observation: When user clicks on the header of sortable column, the search results are not sorted | Bug | Medium | Fixed | 13/03/2018 Wensi | v0.5 |  |  | #70.mp4 |  |  | 02.04.2018 QA: Asset page is showing loading process for infinite time
71 | General | A/C/S | Observation: Create Asset/Staff: User is able to create a record whose expiry date is earlier than current date Expectation: Expiry date must be later than current date | Issue | Medium | Closed | 13/03/2018 Wensi | v0.5 |  |  |  |  | QA: Bug fixed , not occurring now | 20/03/2018 QA: Bug fixed , not occurring now
72 | Staff | Expiry Calendar | Observation: Some expiry dates are not shown on expiry calendar | Bug | Medium | Open | 13/03/2018 Wensi | v0.5 |  |  | #72.png | Hitesh
73 | Staff | Create | Observation: Create/Update Staff: if some staff's info are empty, the text fields will be shifted up. Expectation: Please make sure text field is remained at the same place | Issue | Medium | Open | 13/03/2018 Wensi | v0.5 | 20.03.18 |  | #73.png | Haris/Jana | QA: Bug still exist - https://www.screencast.com/t/ooP5AxnTJI Note: not able to change as Reopen so changed to open | 20/03/2018 QA: Bug still exist - https://www.screencast.com/t/ooP5AxnTJI Note: not able to change as Reopen so changed to open
74 | General | A/C/S | Observation: Update Asset/Staff/Contrat: User is unable to download, upload or remove file Expectation: User shall be able to upload, download, and remove files in edit page | Issue | Medium | Open | 13/03/2018 Wensi | v0.5 |  |  | #74.png |  | Need to check on customer machine QA: Not occurring at our end | 20/03/2018 Need to check on customer machine QA: Not occurring at our end
75 | Settings | Asset Types | Observation: The workflow of add asset type, add asset sub type is not very intuitive… can try to improve the workflow? | Issue | Medium | Open | 13/03/2018 Wensi | v0.5 |  |  | #75.mp4 | Haris |  | 20/03/2018 Discuss with client
76 | General | Consistency | Observation: User: the phone number in create user page and the phone number in user list have different format. E.g. "+65 8503 5450" in create/edit/view page and "6585858585" in user list Expectation: Please ensure format are consistent | Issue | Low | Closed | 14/03/2018 Wensi | v0.5 | 20.03.18 |  |  |  | QA- Issue fixed | 20/03/2018 QA- Issue fixed
77 | UserGroup | User | Observation: User List: created by/date, last modified by/date are displayed in user list. Expectation: created by/date, last modified by/date are not required in user list. Check URS | Issue | Medium | Closed | 14/03/2018 Wensi | v0.5 | 20.03.18 |  | #77.png | Haris
78 | General | A/C/S | Search Contract/Asset/Staff: "there will be an option for user to choose additional fields to be displayed, or hide existing fields in the asset list" Please advise whether this feature is implemented, or how to test this feature. | Issue | Medium | Open | 14/03/2018 Wensi | v0.5 |  |  |  | Haris/Janardhan | Not implemented
79 | General | Err/Alert Msg | Observation: in create/update page, sometimes user are unable to click the submit button because mandatory fields are not keyed in, however, no error message is shown on screen to advise user why he cannot submit the form. Expectation: please display meaningful validation error message on create/update page. this is helpful especially when user keys in data in a long page. | Issue | Medium | Open | 14/03/2018 Wensi | v0.5 |  |  |  |  | Discuss with client
80 | General | Err/Alert Msg | Observation: Sometimes, if submitted form has validation error, the error will be displayed after user submit the form and redirected back to home home page. E.g. if user attempts to create user with duplicate user name, he will be redirected back to user list, and error message "User already exists" is shown on user list. Expecation: If submitted form has validation error, the error shall be shown next to the erroneous field on the create/edit page. So that user knows which field is wrong, and he has the chance to correct field. | Issue | Medium | Open | 14/03/2018 Wensi | v0.5 |  |  |  | Haris | Review and fix if occurring QA: Bug is occurring
81 | UserGroup | User | View My Profile Details: please advise whether this feature has been implemented as stated in URS 22/03/2018 URS 6.1.2.4 View My Profile Details is not implemented | Issue | Medium | Closed | 14/03/2018 Wensi | v0.5 |  |  |  |  | Not Implemented |  | 29/03/2018 QA: Now my profile page gets implemented.
82 | UserGroup | Group | Observation: Add/Update group: unable to click checkbox when add role to group, or add group admin to the group, unable to create/update group | Bug | High | Closed | 21/03/2018 Wensi | v0.6 | 21/03/2018 Wensi | v0.6.3 | #82.mp4 |  | 21/03/2018 tested and passed, close
83 | General | A/C/S | Observation: Create Asset/Contract/Staff Unable to upload files | Bug | High | Closed | 2018-03-21 | v0.6 | 21/03/2018 Wensi | v0.6.3 | #83.mp4 |  | 21/03/2018 tested and passed, close
84 | Contract | Create | Observation: "Officer in Charge" and "Reviewer List" are empty. Unable to create a contract record | Bug | High | Closed | 2018-03-21 | v0.6 |  |  | #84.mp4 |  |  | QA: Bug is fixed on v0.7.3, not occurring at our end
85 | Auth | Login | Observation: A user, who is valid in ldap but not registered in r365, attempts to login r365. Result: user is unable to login, however, no error message is shown on screen. Expectation: Please display meaningful error message on screen | Bug | Medium | Open | 2018-03-22 | v0.6.3 |  |  | #85.mp4 | Haris/Srikanth
86 | UserGroup | User | Observation: Inactivated user is not shown on user list. Expectation: Inactivated user shall be available in user list, user shall be able to search active/inactive user | Issue | Medium | Closed | 22/03/2018 Wensi | v0.6.3 |  |  | #86.mp4 | Srikanth |  |  | 02.04.2018 QA: Issue is fixed now
86 | UserGroup | User | Observation: URS 6.1.2.5 Search User is not implemented | Issue | Medium | Reopen | 22/03/2018 Wensi | v0.6.3 |  |  |  | Janardhan/Jenish |  |  | 29/03/2018 QA:https://www.screencast.com/t/rz8IjsDe 1. Is this be Advanced Search? 2. Department field is still missing
87 | UserGroup | User | Observation: "Department" is missing in Create/Update/View user page Expectation: Department is required according to URS | Bug | High | Closed | 22/03/2018 Wensi | v0.6.3 |  |  | #87.png | Srikanth/Haris |  |  | 02.04.2018 QA: Issue is fixed now
88 | UserGroup | User | Observation: Following requirement in URS Section 6.1.2.2 Update User is not implemented. "A user cannot be inactivated if he is a key role (e.g. Overall Group / User Administrator, Group Administrator of an active user group, Officer-In-Charge of an active contract, reviewer of an active contract, etc...)" | Issue | High | Closed | 22/03/2018 Wensi | v0.6.3 |  |  |  | Haris/Srikanth |  | Yet to be implmented | 02.04.2018 QA: Issue is fixed now
89 | UserGroup | User | Observation: "Department" is missing in Search result. Expectation: "Department" shall be available in search result | Bug | Medium | Closed | 22/03/2018 Wensi | v0.6.3 |  |  |  | Srikanth |  |  | 02.04.2018 QA: Issue is fixed now
90 | General | Coding | Observation: In some db tables, id is not in sequence. Question: How is the id generated? Why id is not a running number such as 1,2,3,4,5,6,…? What is the rational? | Clarification | High | Open | 22/03/2018 Wensi | v0.6.3 |  |  | #90.png | Hitesh |  | We are using Hibernate Sequence which is generic to all tables.
91 | UserGroup | User | Observation: Sometimes, a overall user admin is unable to see User&Group tab | Bug | Medium | Closed | 22/03/2018 Wensi | v0.6.3 |  |  | #91.mp4 #91_db_records.xlsx | Haris/Srikanth |  |  | 29/03/2018 QA: Issue is fixed
92 | UserGroup | General | Observation: Group admin role cannot be granted the access "Notification CC" Expectation: URS 6.1.3.1 Create User Group "Group Administrator will be a default role for any group. By default, a Group Administrator has all access rights except for “Notification CC”." the default access right setup for group admin is all except for Notification CC. However, user shall still be able to update this default access setting, such as grant Group Admin Notification CC access | Issue | Medium | Closed | 22/03/2018 Wensi | v0.6.3 |  |  | #92.png | Haris |  | Will give with CR | 02.04.2018 QA: Issue is fixed now
93 | UserGroup | Group | Observation: Following requirements of URS 6.1.3.3 Update User Group is not implemented "Activate / Inactivate User Group In the update user group page, a user group can be activated / inactivated through “Active” radio button. A user group cannot be inactivated if there are active reminders inside the group. " | Issue | Medium | Closed | 22/03/2018 Wensi | v0.6.3 |  |  | #93.mp4 | Haris/Srikanth |  |  | 02.04.2018 QA: Issue is fixed now
94 | UserGroup | Group | Observation: Created By, Created Date, Last Modified By, Last Modified Date is missing from view, update page Expectation: Created By, Created Date, Last Modified By, Last Modified Date shall be shown in view, udpate pages. see URS | Bug | Medium | Closed | 22/03/2018 Wensi | v0.6.3 |  |  |  | Haris |  |  | 02.04.2018 QA: Issue is fixed now
95 | UserGroup | Group | Observation: Search User Group: Unable to search user group by field "Active" Expectation: See URS section 6.1.3.5 Search User Group | Issue | Medium | Closed | 22/03/2018 Wensi | v0.6.3 |  |  |  | Haris/Janardhan |  |  | 02.04.2018 QA: Issue is fixed now
96 | Asset | Search, Sort, Filter | Observation: User Group is not shown in search result. Wrong column header name: Status (shall be active) Expectation: See URS section 6.3.8 Search Asset | Issue | Medium | Closed | 22/03/2018 Wensi | v0.6.3 | 26.03.2018 |  | #96.png | Janardhan/Haris |  | QA: Fixed on v0.7.3
97 | General | A/C/S | Observation: In search result, expiry date format is wrong. Expectation: Refer to URS | Issue | Low | Open | 22/03/2018 Wensi | v0.6.3 |  |  | #97.png | Janardhan
98 | General | A/C/S | Observation: Created By, Created Date, Last Modified By, Last Modified Date is missing from view, update, review page Expectation: Created By, Created Date, Last Modified By, Last Modified Date shall be shown in view, udpate, and review page. see URS | Issue | Low | Open | 22/03/2018 Wensi | v0.6.3 |  |  | #98.png | Janardhan/Hitesh
99 | Asset | View | Observation: In view asset page, "Active" and "Status" are combined into one field "Active/Expired" Expectation: "Active" and "Status" shall be separated fields. | Issue | Medium | Open | 22/03/2018 Wensi | v0.6.3 |  |  | #99.png | Hitesh
100 | Asset | Record Summary | Observation: Asset summary doesn't tally with the assets in result list | Bug | Medium | Open | 22/03/2018 Wensi | v0.6.3 |  |  | #100.mp4, #100_db.zip | Hitesh
101 | Staff | Search, Sort, Filter | Observation: "OFO / SFO" and "Local Crew" is missing in search filter Expectation: Refer to urs | Issue | Medium | Open | 22/03/2018 Wensi | v0.6.3 |  |  | #101.png | Hitesh
102 | Staff | Search, Sort, Filter | Observation: "Local Crew" and "User Group" are missing is search results "Reference No" shall not been shown in search results Expectation: See urs Section 6.4.8 Search Staff Monitor Record | Issue | Medium | Open | 22/03/2018 Wensi | v0.6.3 |  |  | #102.png | Hitesh/Janardhan
103 | Staff | Download | Observation: Search results are not empty, however, downloaded staff search results is empty. | Bug | High | Closed | 22/03/2018 Wensi | v0.6.3 |  |  | #103.png #103_Staff_export_1521691082084.xlsx | Janardhan |  | QA: Bug fixed on v0.7.3
104 | UserGroup | Group | Observation: Sometimes group list is empty, browser console has bug | Bug | High | Closed | 22/03/2018 Wensi | v0.6.3 |  |  | #104.mp4 #104_db.zip | Haris/Srikanth |  |  | 29/03/2018 QA: Issue is fixed
105 | Settings | Staff Default Rem | Observation: First Reminder and Second Reminder are mandatory Expectation: First Reminder, Second Reminder shall be optional. User may create a record type without default remdiner setup. Refer to urs and "UI Feedback 20171222.pdf" | Issue | Medium | Closed | 22/03/2018 Wensi | v0.6.3 |  |  | #105.mp4 | Hitesh/Janardhan |  |  | 02.04.2018 QA: Issue is fixed now
106 | Settings | General | Observation: Staff/Asset/Contract default reminder. If user doesn't set up default Third Reminder, Thrid Reminder will be 0. Expectation: If user doesn't set up a default reminder, then it shall be empty. When create a record, the corresponding reminder dates shall be empty as well. | Issue | Medium | Fixed | 22/03/2018 Wensi | v0.6.3 |  |  | #105.mp4 | Hitesh/Janardhan |  |  | 02.04.2018 QA: Checked for Setting > Staff working fine but unable to check for Asset(blocked with creation of Asset Type and Sub Type) Contract issue persist - https://www.screencast.com/t/9aHPgbqA
107 | Settings | Staff Particulars | Observation: View staff: Local Crew is always empty | Bug | Medium | Closed | 22/03/2018 Wensi | v0.6.3 |  |  | #107.mp4 | Hitesh/Janardhan |  |  | 02.04.2018 QA: Issue is fixed now
108 | Settings | Staff Particulars | Observation: View/Update staff particulars: Created By, Create Date, Last Modified By, Last Modified Date is not shown in view and update page. | Bug | Low | Closed | 22/03/2018 Wensi | v0.6.3 |  |  |  | Hitesh/Janardhan |  |  | 02.04.2018 QA: Issue is fixed now
108 | Settings | Staff Particulars | Observation: Fields shown in search results is not tally with urs | Issue | Medium | Open | 22/03/2018 Wensi | v0.6.3 |  |  |  | Hitesh/Janardhan
109 | Staff | Create | Observation: Local Crew is missing Section is displayed wrongly (showning id) typo: OFS/SFC should be changed to OFO/SFO | Bug | Medium | Reopen | 22/03/2018 Wensi | v0.6.3 |  |  | #109.PNG | Hitesh/Janardhan |  |  | 29/03/2018 QA: Issue still exist - https://www.screencast.com/t/ZO2lUXu49Q 1. Section fields is blank(not fetching data) 2. local Crew field is still not there 3. Typo is fixed
110 | Staff | Update | Observation: Sometimes user is unable to click the submit button, even when all data are valid. | Bug | Medium | Closed | 22/03/2018 Wensi | v0.6.3 |  |  | #110.mp4 | Hitesh/Janardhan |  |  | 29/03/2018 QA: Issue is not occurring at our end
111 | Staff | Delete | Observation: Sometimes unable to delete a staff record. | Bug | High | Reopen | 22/03/2018 Wensi | v0.6.3 |  |  | #111.mp4 | Hitesh/Janardhan |  |  | 29/03/2018 QA: At our end also we are not able to delete one staff from the list- https://www.screencast.com/t/2lNDXQUDIAx9
112 | Staff | Create | Observation: When create a new staff record, search of Staff Code/Staff Name doesn't support wildcard search Expectation: Refere to urs Section 6.4.1 Create Staff Monitor Record "E.g. If user searches “h”, “L” or “Hl”, etc., “Harry Lim (HL)” will be shown in search as you type dropdown list. When user enters Staff Code and hits enter key, or clicks “Harry Lim (HL)”, all other staff particulars will be auto populated according to Staff Code. If staff is not found, meaningful error message shall be displayed. Staff Code is unique in R365" | Issue | Medium | Open | 22/03/2018 Wensi | v0.6.3 |  |  | #112.mp4 | Hitesh/Janardhan
113 | General | A/C/S | Observation: Expiry date of active record is not shown in calendar Expectation: URS: "In staff reminder home page, a calendar of current month will be displayed on the top of the page. Expiry date(s) of all the active staff monitor record(s) in the login user’s group(s) will be highlighted in red on the calendar. If user clicks a date on expiry calendar, active staff monitor record(s) expiring on that date will be shown in search result. " | Issue | Medium | Open | 22/03/2018 Wensi | v0.6.3 |  |  | #113.png | Hitesh/Janardhan |  | Jana: Please verify and mark as Fixed
114 | Settings | Location | Observation: Created_at, last_modified_at are always null in R365.location table | Bug | Low | Open | 23/03/2018 Wensi | v0.6.4 |  |  | #114.png |  | Newly Added in V1.05
115 | Settings | Location | Observation: Previous and Next button in Location list is not working | Bug | Medium | Closed | 23/03/2018 Wensi | v0.64 |  |  | #115.mp4 |  | Newly Added in V1.05 |  | 02.04.2018 QA: Issue is fixed now
116 | Settings | Asset Types | Observation: Asset Types are listed in random order. Expectation: Please list asset in alphabetical ascending order (start from 0 to 9, a to z) | Enhancement | Medium | Open | 23/03/2018 Wensi | v0.6.4 |  |  | #116.mp4 |  | Newly Added in V1.05
117 | Asset | Asset Types | Observation: Asset Types in dropdown list are listed in random order. Expectation: Please list asset in alphabetical ascending order (start from 0 to 9, a to z) | Enhancement | Medium | Open | 23/03/2018 Wensi | v0.6.4 |  |  | #117.mp4 |  | Newly Added in V1.05
118 | Settings | Asset Types | Observation: "+" sign in expandable in not updated to "-" when the panel is expanded. Expectation: "+" shall change to "-" when panel is expanded, "-" shall change to "+" when panel is closed | Bug | Low | Open | 23/03/2018 Wensi | v0.6.4 |  |  | #118.mp4 |  | Newly Added in V1.05
119 | Contract | Create Contract | Observation: Sometimes, user can select himself as the reviewer when create a contract, Expectation: "Reviewer cannot be the login user". See URS | Issue | High | Open | 02/04/2018 Wensi | v0.7.7 |  |  | #119_1.mp4 #119_2.mp4 | Archana | Newly Added in V1.05 | #119_1.mp4 --> user can select himeself as the reviewer #119_2.mp4 --> user cannot select himeself as the reviewer #119_db.zip
120 | Contract | Review Contract | Observation: Sometimes, user is able to review/reject a contract, even though he is not the reviewer. Expectation: Only the users in reviewer list shall be able to review/reject a contract | Bug | High | Open | 02/04/2018 Wensi | v0.7.7 |  |  | #120_1.mp4 #120_db.zip | Archana | Newly Added in V1.05 | #120_1.mp4 --> non reviewer can review/reject a contract #120_2.mp4 --> non reviewer cannot review/reject a contract
121 | Contract | Update Contract | Observation: In Edit Contract Page, all contents are read only Expectation: Contract shall be editable in update contract page | Bug | High | Open | 02/04/2018 Wensi | v0.7.7 |  |  | #121.mp4 | Archana | Newly Added in V1.05 | refer to #120_db.zip for data in database
122 | Contract | Delete Contract | Observation: In review page, message "This Contract is createdby rs365_user4 on 4/2/18, 11:38 AM. Please verify" is shown for adeletedcontract (pending verification). Expectation: Message such as "This contract isdeletedby xxx on xxxxxxx. Please verify." shall be shown fordeletedcontract. | Bug | High | Open | 02/04/2018 Wensi | v0.7.7 |  |  | #122.mp4 | Srikanth | Newly Added in V1.05 | please include exception details in Reminder.log
123 | Contract | Verify Contract Deletion | Observation Verify a deleted contract hit exception | Bug | High | Open | 02/04/2018 Wensi | v0.7.7 |  |  | #123.mp4 #123_Reminder.log | Srikanth | Newly Added in V1.05 | refer to #120_db.zip for data in database
124 | Dashboard | Dashboard | Observation: Axis unit is 0.5 Expectation: Axis unit shall be integer | Issue | Medium | Open | 02/04/2018 Wensi | v0.7.7 |  |  | #124.png | Janardhan | Newly Added in V1.05
125 | Others | Reminder365 URL | Observation: current r354 url is: http://rs365-test.marine.psa:8080/Reminder365 Expectation: please remove port number 8080: http://rs365-test.marine.psa/Reminder365 | Issue | Medium | Open | 02/04/2018 Wensi | v0.7.7 |  |  |  | Hitesh | Newly Added in V1.05

## Sheet1 (hidden)
General Issue
Closing the tab does not kill the session for our application. E.g. when the customer logout form marine portal and login as another user, our application will retrieve the old session upon click another page