## Info
Project: | Reminder365 Web App
Test URL: | http://rs365-test.marine.psa:8080/Reminder365/
http://10.114.72.44:8080/Reminder365/
Release History
Version | Released By | Release Date
20180206 | Sourabh | 20180206
Revision History
Version | Prepared By | Date
1.0 | Wensi | 07/02/2018

## Summary
Issue (open) | [13 empty] | Bug (open)
Enhancement (open) | [13 empty] | Clarification (open)
CR (open)
Feedback Summary
Category | Issue | [6 empty] | Bug | [6 empty] | Enhancement | [6 empty] | Clarification | [5 empty] | CR
MainMod \ Status | Open |  |  | Fixed | Closed | Invalid | Total | Open |  |  | Fixed | Closed | Invalid | Total | Open |  |  | Enhanced | Closed | Invalid | Total | Open |  |  | Clarified | Invalid | Total | Open |  |  | Invalid | Total
Severity | High | Medium | Low |  |  |  |  | High | Medium | Low |  |  |  |  | High | Medium | Low |  |  |  |  | High | Medium | Low |  |  |  | High | Medium | Low
Auth | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UserGroup | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contract | 4 | 8 | 0 | 0 | 0 | 0 | 12 | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Asset | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Staff | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Settings | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Notification | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Dashboard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Performance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
General | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Others | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 7 | 8 | 0 | 0 | 0 | 0 | 15 | 7 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SubMod | MainMod
| Auth | UserGroup | Contract | Asset | Staff | Settings | Notification | Dashboard | Performance | General | Others
| General | General | General | General | General | General | General | General | General | General | General
| Login | User | Create | Create | Create | Contract Default Rem | Reminder | Summary by Module |  | Logging
| Logout | Group | View | View | View | Asset Default Rem | Expiry | Summary by User Group |  | Coding
| Session Timeout | Access Control | Update | Update | Update | Asset Types | Maker Checker | Expiry Calendar |  | Database
|  | My Group | Delete | Delete | Delete | Asset Locations
|  |  | Renew | Renew | Renew | Staff Default Rem
|  |  | MakerChecker | Expiry Calendar | Expiry Calendar | Staff Particulars
|  |  | MC-Add | Record Summary | Record Summary | Staff Record Types
|  |  | MC-Update | Search, Sort, Filter | Search, Sort, Filter
|  |  | MC-Delete | Download | Download
Expiry Calendar
Record Summary
Search, Sort, Filter
Download
Status | General: Category
| Issue | Bug | Enhancement | Clarification | CR
| Open | Open | Open | Open | Open
| Fixed | Fixed | Enhanced | Clarified | Invalid
| Closed | Closed | Closed | Invalid
| Invalid | Invalid | Invalid
Severity
High
Medium
Low

## R365
# | Module |  | Description | Category | Severity | Status | Test |  | Verify |  | Test Evidence | Comments
| Main | Mod |  |  |  |  | Date & By | Release | Date & By | Release |  | PSAM | Saksoft
1 | Auth | Login | Observation: when user login, password is printed in clear text Expectation: password should not be printed in clear text | Issue | High | Open | 06/02/2018 Wensi | 20180206 |  |  | #1.PNG
2 | Auth | Login | Observation: At login page, if user hasn't keyin username / password, user is not allowed to click LOGIN button. However, error message is not clearly shown. --> User may not be clear about what is happening, Expectation: App should show error message clearly when user hasn't keyed in proper username / password. | Enhancement | Medium | Open | 06/02/2018 Wensi | 20180206 |  |  | #2.PNG
3 | Auth | General | Observation: "Forgot Password?" dialogue will only be closed when user clicks the "x" icon Expectation: "Forgot Password?" dialogue should also be closed when user click outside of the dialogue. | Enhancement | Medium | Open | 06/02/2018 Wensi | 20180206
4 | Auth | General | Observaztion: When user keys in wrong username / password, and then click LOGIN button repeatedly, the same error messages are shwon on the screen repeatedly Expectation: Duplicate error message should not be shown on screen | Enhancement | Medium | Open | 06/02/2018 Wensi | 20180206 |  |  | #4.PNG
5 | Auth | Login | Observation: Username and password is always automatically remembered by browser, user has no option to unsave the password Expectation: Provide a checkbox for user to choose to save or unsave password at login page. | Issue | High | Open | 07/02/2018 Wensi | 20180206 |  |  | #5.png
6 | General | Record Summary | Observation: When click the arrow icon of the summary boxes (e.g. "No. of Contracts Expired", "No. of Contracts Expiring This Month","No. of Contracts Expiring Next Month", etc...), user will be redirected to login page | Bug | High | Open | 07/02/2018 Wensi | 20180206
7 | General | General | Observation: Whenever user clicks browser refresh button (e.g. on dashboard, contract list page, etc), user will see "Access Denied" error Expectation: User shall be able to refresh page | Issue | High | Open | 07/02/2018 Wensi | 20180206 |  |  | #7.PNG
8 | Contract | General | Observation: Calendar popup is only closed when user clicks on the calendar icon, but not closed when user click on outside of the input field. Expectation: Expect calendar pop up to be closed when calendar popup lose focus | Enhancement | Medium | Open | 07/02/2018 Wensi | 20180206 |  |  | #8.PNG
9 | Contract | General | Observation: no error message is shown when reminder dates are later than expiry date. User is able to create a contract reminder whose reminder dates are later than expiry dates Expectation: 1st, 2nd and 3rd reminder dates shall not be later than expiry date. Expriy message shall be shown properly | Bug | High | Open | 07/02/2018 Wensi | 20180206 |  |  | #9.PNG
10 | Contract | General | Observation: Confirmation message "Contract has been added to Reminder365 successfully" is shown when a contract is created successfully. However, contract reminder number is not included in confirmation message. Expectation: Contract reference number shall be included in confirmation message whenever possible. Please show confirmation message after contract is added/update/deleted/resubmitted ... in following format Contract {contract ref number} is {action}ed and waiting for verification. E.g. Contract CONT1234 is added and waiting for verification. Contract CONT1234 is edited and waiting for verification. Contract CONT1234 is deleted and waiting for verification. Contract CONT1234 is resubmitted and waiting for verification. Contract {contract ref number} is {action}ed successfully E.g. Contract CONT1234 is verified successfully. Contract CCNT1234 is rejected successfully. | Issue | Medium | Open | 07/02/2018 Wensi | 20180206 |  |  | #10.PNG
11 | Contract | General | Observation: in create reminder page, user is unable to click "submit" button if there are validation error. No error message is shown. User is unclear about what is happening. Expectation: Allow user to click "SUBMIT" button when there is invalid data, app shall show error message properly after user clicks "SUBMIT" button | Issue | Medium | Open | 07/02/2018 Wensi | 20180206
12 | Contract | Expiry Calendar | Observation: Expiry calendar function is not ready yet - not default to current month - < > button is not working - dates and weekdays don't match - etc | Issue | High | Open | 07/02/2018 Wensi | 20180206 |  |  | #12.PNG
13 | Contract | Expiry Calendar | Observation: There is a "-" and "x" icon on Expiry Calendar. However, there is not effect when user clicks "-" and "x" icon Expectation: "-" and "x" is not required | Issue | Medium | Open | 07/02/2018 Wensi | 20180206 |  |  | #13.PNG
14 | Contract | General | Observation: When user clicks Submit button on create page, following confirmation dialogue is shown: "Contract "abc" will be created! Confirm to continue. [NO][YES]" Expectation: Please show confirmation dialogue in following format: "You are going to {action} Contract {contract_num}. Click OK to continue." [CANCEL] [OK] e.g. You are going to Add Contract CONT1234. Click OK to continue. [CANCEL] [OK] You are going to Edit Contract CONT1234. Click OK to continue. [CANCEL] [OK] You are going to Delete Contract CONT1234. Click OK to continue. [CANCEL] [OK] You are going to Verify Contract CONT1234. Click OK to continue. [CANCEL] [OK] You are going to Reject Contract CONT1234. Click OK to continue. [CANCEL] [OK] | Enhancement | Medium | Open | 07/02/2018 Wensi | 20180206
15 | Contract | General | Observation: Fields "Savings Currency & Contract" and "Contract Currency & Value" require 2 decimal places. However, the place holders for them are "000" and "00" respectively, which might be confusing to user Expectation: Please use placeholder "00.00" for these two fields | Issue | Medium | Open | 07/02/2018 Wensi | 20180206 |  |  | #15.PNG
16 | Contract | General | Observation: Confirmation dialogue "You have unsaved data!, Do you want to leave?" is shown if user going to leave current edit page. Expectation: Display following message in confirmation dialogue instead: "You are going to leave this page without saving any information. Click OK to continue. [CANCEL] [OK]" | Enhancement | Medium | Open | 07/02/2018 Wensi | 20180206
17 | Contract | Create | Observaton: In create page, "Active" is default to "NO" Expectation: Please default "Active" to "Yes". See URS 6.2.1 | Issue | Medium | Open | 07/02/2018 Wensi | 20180206
18 | Contract | MakerChecker | Observation: Checker is able to edit details of a "pending-verification" contract Expectation: A checker shall only be able to verify or reject a contract. He shall not be able to edit the contract details | Issue | High | Open | 07/02/2018 Wensi | 20180206
19 | Contract | General | Observation: Created By, Created Date, Last Modified By, Last Modified Date is missing from view, update, review page Expectation: Created By, Created Date, Last Modified By, Last Modified Date shall be shown in view, udpate, and review page. see URS | Issue | High | Open | 07/02/2018 Wensi | 20180206
20 | Contract | General | Observation: For all Date fields, placeholders are DD/MM/YYYY. However, after pickup a date from calendar, date are in YYYY-MM-DD format Expectation: Please make placeholder and user input consistent | Issue | Medium | Open | 07/02/2018 Wensi | 20180206 |  |  | #20.PNG
21 | Contract | MakerChecker | Observation: When click "Reject" button on reivew contract page, Following popup will be shown: ------------------------------------------------------------------------------ REJECT MESSAGE Contract Title: (readonly) Contract Reference Number: (readonly) Message To: (textfield) Remarks: (textarea) [SEND MESSAGE] ------------------------------------------------------------------------------ Analysis: Rejection Remarks will be shown in contract review page after a contract is rejected, rather than notification email (see email template), so "Message To" field and "Send Message" button are not relevent. Expectation: when user clicks "Reject" button, app shows following popup box ------------------------------------------------------------------------------ Reject Contract You are going to reject Contract ContNumABC. Please key in Rejection Remarks, and click OK to continue. Rejection Remarks: (textarea) [CANCEL] [OK] ------------------------------------------------------------------------------ | Issue | Medium | Open | 07/02/2018 Wensi | 20180206
22 | Contract | MakerChecker | Observation: In review contract page, message such as "This contract is created by Harry Lim on 07/02/2018 13:45. Please verify" is not shown. Expectation: Please display mesasge on review contract page in following format: This contract is {action}ed by {maker} on {date time}. Please review and verify. E.g. This contract is added by Harry Lim on 07/02/2018 15:47. Please review and verify. | Issue | Medium | Open | 07/02/2018 Wensi | 20180206
23 | Contract | MC-Add | Observation: Step1: maker adds contract Step2: checker rejects contract Step3: maker updates and resubmit contract Results: in contract review list, there is one contract with status "Rejected" and one contract with status "New" Step4: maker delete "Rejected" contract Results: in contract review list, there is one contract with status "Deleted" and one contract with status "New" Expectation: At Step3: the resubmitted contract shall overwrite the "Rejected" contract, so in contract review list, there is only one "New" contract with updated details. At Step4: after maker delete the "Rejected" contract, this rejected contract shall be removed from the system. | Issue | High | Open | 07/02/2018 Wensi | 20180206 |  |  | #23.PNG
24 | Contract | MC-Add | Observation: Step1: maker adds contract Step2: checker verified contract --> when user clicks "verify" button, there is no confirmation dialogue shown for user to confirm his action Expectation: Please show confirmation dialogue for user to confirm his action. refer to #14 | Bug | High | Open | 07/02/2018 Wensi | 20180206
25 | Contract | MC-Update | Observation: Step1: maker creates contract Step2: checker verifies contract Step3: maker updates contract (update contract ref number) --> result: the original contract is missing in contract list. Expectation: The original contract shall still be in contract list, and the updated contract shall be in contract review list. see urs 6.2.6.2 | Bug | High | Open | 07/02/2018 Wensi | 20180206
26 | Contract | MC-Update | Observation: Step1: maker creates contract Step2: checker verifies contract Step3: maker updates contract (update contract title) Step4: checker verifies contract --> result: both the original contract and updated contract exist in contract list Expectation: Only the updated contract shall be shown in the contract list after the updated details are verified. | Bug | High | Open | 07/02/2018 Wensi | 20180206
27 | Contract | MC-Delete | Observation: Step1: maker creates contract Step2: checker verifies contract Step3: maker deletes contract --> result: the original contract is missing in contract list. Expectation: The original contract shall still be in contract list, and the deleted contract shall be in contract review list. see urs 6.2.6.3 | Bug | High | Open | 07/02/2018 Wensi | 20180206
28 | Contract | MC-Delete | Observation: Step1: maker creates contract Step2: checker verifies contract Step3: maker deletes contract Step4: checker verifies contract deletion --> result: the original contract appears in contract list again.. Expectation: After contract deletion is verified, the contract shall be removed from the system | Bug | High | Open | 07/02/2018 Wensi | 20180206

## Sheet1 (hidden)
General Issue
Closing the tab does not kill the session for our application. E.g. when the customer logout form marine portal and login as another user, our application will retrieve the old session upon click another page